## Detailed project Plan
Stage |  | Stage overview | Expected duration (days) | Self-migration project activities
1 | Initial preparations and considerations | This stage prepares the organisation to implement migration to NHSmail and affirms the organisation's high-level commitment to project delivery and decommissioning of local email service. | 10 | Implementation preparation and organisational sign-off
Email feedback@nhs.net to confirm migration intent
Complete discovery questionnaire
Check that your Organisation Data Service (ODS) code is setup. - http://nww.hscic.gov.uk/ods/enquiries/
Draft business case and take into account integrated applications on current email service
Gain executive or senior management sign-off
GATEWAY 1
2 | Initiation | This stage guides the organisation to perform effective pre-implementation analysis of existing infrastructure and data. Key outputs at this stage are project plan and Project Initiation Document (PID). | 10 | Resource
Assign project manager
Identify project staff
Analyse existing email infrastructure
Analyse individual, generic and non-user mailboxes, calendars, email rules, distribution lists and users with mobile access to NHSmail
Identify users to be migrated and consider whether all users on the mail server be migrated?
Consider migrating users in group phases - consider what or how many these groups are and the dates they will be migrated?
Reconciliation Process
Map mail addresses to @nhs.net including user and generic accounts
Resolve mapping for non-user specific email addresses e.g. generic mailboxes
Alerts and automated messaging - identify and plan work stream
Review local email data
Check user mailboxes comply with quotas, check against blocked attachments, allowed file types and attachment size
Plan how to manage legacy data
Develop project plan and consider milestones, risks, issues and reporting
Complete, agree and share PID with Implementation Support Manager (ISM)
GATEWAY 2
3 | Running the project | This stage helps the organisation to enhance project planning and project delivery ensuring particular focus to key areas. | 15 | Initial project planning
Confirm approach and/or methodology for managing legacy data
Communications plan including the frequency and content of messages to staff
Distribute NHSmail welcome message
First Announcement
Intranet update
Second Announcement
Activate 'out of office' messages
FAQ and Mail box advice
Mail revised dates to all staff
Create briefing presentation
Team brief via senior managers meeting
Design, create and distribute posters
Communicate folder mapping and merging process. Consider guidance on renaming of NHSmail folders to prevent data merging where users wish to do so.
Implementation support - Part of communication. Assurance and information of the local Trust support available
Email migration schedule and activities
Preparation email (Groups 1, 2 3, etc)
Corporate communications changes defined and planned for cut-over
Implement corporate communication changes
Distribution list (DL) - Part of communication
Shared mailboxes - Part of communication
Develop processes to feed into communications plan
Training plan
Prepare advance user training , bulletins, guidelines, help sheet, etc.
Prepare final user training bulletin, first use guidelines. i.e setting up permissions calendar share, etc.
Make training available via intranet
Training (Session 1, 2, 3, etc)
Prepare and deliver NHSmail for mobile devices training
Training refresh for LOAs
Agree arrangements for out of hours help desk
Planning for mobile phones
Notifysych / ActiveSync for Blackberry's
Check Sync for new mobile devices
Decision on Mobile devices policy and use (BYOD allowed?)
Configuration plan - support or collect devices for configuration / rollout
Access method
Check email co-existence design to understand mail routing during period of a phased migration.
Trust to include implications of co-existence design into communications plan.
Confirm help desk escalation routes for pilot and migration phases.
Roll out desktop application updates (Outlook 2003)
If using Outlook 2010 test the config settings if creating dual exchange profile for local exchange and NHSmail.
Identify shared mailboxes and include in connector and reconciliation spreadsheet
Identify email accounts used in applications and as system alerts - update connector and reconciliation spreadsheet
Confirm owners for generic mailboxes
Identify corporate distribution lists - they will have to be recreated on NHSmail
Register generic accounts
Agree additional post migration helpdesk cover (including out of hours)
Set up NHSmail Connector
Contact helpdesk@nhs.net to set up Connector
Test Connector
Update local processes and policies
Revise, gain approval and publish local email policy (pay due regard to NHSmail Acceptable Use Policy (AUP) if required
New starter process
Leavers process
Quality review
Plan to continually provide up to date e-mail address list of both trust and NHSmail users. Both groups of users need to know who is in which group and the e-mail addresses
Plan mop-up activities
Contingency period
Contingency migration procedures and planning
Clear communications plan to cover contingency
Confirm and agree migration dates and registration slot on pipeline with ISM
GATEWAY 3
4 | Migration Readiness Assessment | This stage readies the organisation for implementation. The stage also includes scope for a pilot to test approach and methodology in preparation for the main migration. | 20 | Pre-pilot activities
Technical testing activities
Confirm all machines are running full Service Pack (SPs) patches etc
Investigate and determine archiving approach
Test archiving process to create archive, archive store and any indexing
Test archive access via Outlook plugin or web client
Test archiving process end to end and make available for comms plan
Check firewall rules to support connection to NHSmail service incl web, LDAP and Auto discover
Check current backup schedule and assess scope for adjusting schedule to avoid clashing with archive activity.
Test the auto-forwarding method from local exchange to NHSmail before use in live migrations.
Test Outlook configuration script - auto discover or separate script for Outlook 2003 clients
Test Outlook configuration script - archive or PST file connection
Technical testing sign-off
NHSmail accounts - user rollout
Create extract from reconciliation spreadsheet for new NHSmail accounts required - note exclude existing a/c
Build schedule for provisioning and rollout of new NHSmail accounts - phased provisioning?
Update system email accounts to NHSmail accounts
Update shared and generic mailboxes to NHSmail accounts
LOA bulk register to create new user accounts using connector populated pending accounts accounts
Run archive tool to build archive
Note plan for co-existence on NHSmail rollout: Starts as soon as NHSmail accounts are active and become visible on NHS Directory
Connector and reconciliation spreadsheet
Review reconciliation spreadsheet with source and target address and process and scheduling document
Match Connector/organisational cutover report with reconciliation spreadsheet
Submit test Connector
Request test Connector to run in production if test run is OK
Reconcile new users and existing NHSmail users
Connector is running in production and uploads data successfully to NHS Directory
Quota management
Initial analysis
Email to high traffic users
Follow up analysis
Follow up email
Identify cases for larger defaults
Specific emails
Specific desk visits
Define final options
Pilot
Distribute NHSmail accounts for users to activate
Ensure users activate in the portal BEFORE using MS Outlook
Support for user activation process
Co-existence use: Users access local service using local client BUT access NHSmail in Portal
Plan cutover events - comms / schedule / support / helpdesk
Start cutover: Auto forward
Run archive tool to build archive
Deploy Group Policy / script to create new mail profile for user in pilot
Configure mail client to link to archive / PST
Import calendar items into live NHSmail account from archive - if required
Setup permissions for shared mailbox shared calendar etc
Post-pilot and mop-up activities
Helpdesk report - outstanding issues / open calls
Risk and issues log
Lessons learned - update comms plan and project plan
Update reconciliation spreadsheet
Organisation sign off for successful Pilot and ready for Main Phase rollout and Bulk Registration
Go/No-Go decision from HSCIC
GATEWAY 4
5 | Roll Out | This stage guides the organisation to implement the bulk migration of users or rollout. | 60 | Main migration - (phased rollout groups 1, 2, 3 etc)
Bulk registration for phase
Distribute NHSmail accounts for users to activate
Ensure users activate in the portal BEFORE using MS Outlook
Support for user activation process
Co-existence use: Users access local service using local client BUT access NHSmail in Portal
Plan cutover events - comms / schedule / support / helpdesk
Start cutover: Auto forward
Run archive tool to build archive
Deploy Group Policy / script to create new mail profile for user in pilot
Configure mail client to link to archive / PST
Import calendar items into live NHSmail account from archive - if required
Setup permissions for shared mailbox shared calendar etc
Ensure communication throughout
Provide updates to ISM regards project progress/status of accounts created and rolled out to users
GATEWAY 5
6 | Post-migration review activity | This stage guides the organisation carry out mop-up and post-migration activities including assessment of implementation success, lessons learnt and benefits evaluation. | 15 | Mop up activities
Helpdesk report - outstanding issues / open calls
Lessons learned - update comms plan and project plan
Update reconciliation spreadsheet
Update NHSmail team with updates for each phase - to allow your ISM to record activity.
Post-migration activities
Provide additional post migration help desk cover
Set up a global “Out of office” to explain that we have moved to NHS mail.
Set up auto forward on Exchange server. This to automatically forward any e-mails sent to a "Trust" address to forwarded to the corresponding NHS address
Maintain auto replies
SMTP mail address in SharePoint if using SharePoint address book
Check process using Connector to update starters and leavers and enrich Directory data
Post-project
Post implementation review
Post project report including users successfully migrated and projected number of accounts required for the next 12 months - share report with ISM
Implement actions arising
Decommission local email server and MTA
Post-implementation
Post-implementation report
Lessons learnt report
Benefits realisation report
In-house email server decommissioning plan
Register interest for additional services
Total duration (days) |  |  | 130

## Priority org possible timeline
|  | Duration (days) | Start | End
Stage1 | Initial preparations and considerations | 10 | 2016-04-18 | 2016-04-29
Stage2 | Initiation | 10 | 2016-05-02 | 2016-05-13
Stage3 | Running the project | 15 | 2016-05-16 | 2016-06-03
Stage4 | Migration Readiness Assessment | 20 | 2016-06-06 | 2016-07-01
Stage5 | Roll out | 60 | 2016-07-04 | 2016-09-30
Stage6 | Post migration review activity | 15 | 2016-10-03 | 2016-10-21