## HV Efforts (hidden)
Orange Implementation Efforts ( Hardening & Security + PreTUPS Version Upgrade )
S No | TASK | Responsibility | Man Days
1 | Prerequisites Check Up | Comviva | 5
2 | Hardware Installation - Servers, Switches, Storage and Tape Drives | Comviva | 9
3 | OS installation | Comviva | 5
4 | LB Configuration | Comviva | 4
5 | Firewall Configuration | Comviva | 3
6 | Switch Configuration | Comviva | 3
7 | Hardening | Comviva | 5
8 | External storage | Comviva/Orange | 3 | 42
9 | Database Activities | Comviva | 5
10 | Application Deployment, Integration & Testing Pretups 6X | Comviva | 23
11 | Load Testing Pretups 6x | Comviva | 3
12 | Application load testing with Live/Test IN and DB | Comviva/Orange | 2
13 | Hardware Handover UAT | Comviva | 4
14 | UAP with Client | Comviva | 12
16 | Trial Migration | Comviva/Orange | 3
17 | Final Migration | Comviva/Orange | 2
18 | Monitoring Period | Comviva | 0
| Total Deployment Days |  | 91
| Weeks |  | 13 | 78 | 91

## HV Deployment Plan (hidden)
Deployment Plan for PreTUPS 6.x. ( Plan for Platform Deployment, Testing and UAT )
S NO. | Task | Details | [7 empty] | Man Days Required | Start Date | End Date | Responsibility | Remarks
1 | Prerequisites Check Up | Physical Verification of Bill of Material (BOM) | Physical Verification of Bill of Material (BOM) | Physical Verification of Bill of Material (BOM) | Physical Verification of Bill of Material (BOM) | Physical Verification of Bill of Material (BOM) | Physical Verification of Bill of Material (BOM) | Physical Verification of Bill of Material (BOM) | Physical Verification of Bill of Material (BOM) | 2 | 2014-01-01 | 2014-01-03 | Comviva/Orange
|  | Un-Packaging of Hardware at Installation Site | Un-Packaging of Hardware at Installation Site | Un-Packaging of Hardware at Installation Site | Un-Packaging of Hardware at Installation Site | Un-Packaging of Hardware at Installation Site | Un-Packaging of Hardware at Installation Site | Un-Packaging of Hardware at Installation Site | Un-Packaging of Hardware at Installation Site | 1 | 2014-01-03 | 2014-01-04 | Comviva/Orange
|  | Cross-Checking With Packing List | Cross-Checking With Packing List | Cross-Checking With Packing List | Cross-Checking With Packing List | Cross-Checking With Packing List | Cross-Checking With Packing List | Cross-Checking With Packing List | Cross-Checking With Packing List | 1 | 2014-01-04 | 2014-01-05 | Comviva/Orange
|  | Validation of availability of Power till the rack by FT/Affiliates (Power till the rack has to be provided by FT) | Validation of availabilty of Power till the rack by FT/Affiliates (Power till the rack has to be provided by FT) | Validation of availabilty of Power till the rack by FT/Affiliates (Power till the rack has to be provided by FT) | Validation of availabilty of Power till the rack by FT/Affiliates (Power till the rack has to be provided by FT) | Validation of availabilty of Power till the rack by FT/Affiliates (Power till the rack has to be provided by FT) | Validation of availabilty of Power till the rack by FT/Affiliates (Power till the rack has to be provided by FT) | Validation of availabilty of Power till the rack by FT/Affiliates (Power till the rack has to be provided by FT) | Validation of availabilty of Power till the rack by FT/Affiliates (Power till the rack has to be provided by FT) | 0.5 | 2014-01-05 | 2014-01-05 12:00 | Comviva/Orange
|  | Rack installation Space and placement check against the solution document | Rack installation Space and placement check against the solution document | Rack installation Space and placement check against the solution document | Rack installation Space and placement check against the solution document | Rack installation Space and placement check against the solution document | Rack installation Space and placement check against the solution document | Rack installation Space and placement check against the solution document | Rack installation Space and placement check against the solution document | 0.5 | 2014-01-05 12:00 | 2014-01-06 | Comviva
[11 empty] | 2014-01-06 | 2014-01-06 | Comviva
2 | Hardware Installation - Servers, Switches, Storage and Tape Drives | Rack installation with PDU with power | Rack installation with PDU with power | Rack installation with PDU with power | Rack installation with PDU with power | Rack installation with PDU with power | Rack installation with PDU with power | Rack installation with PDU with power | Rack installation with PDU with power | 1 | 2014-01-06 | 2014-01-07 | Comviva
|  | Server installation in Rack | Server installation in Rack | Server installation in Rack | Server installation in Rack | Server installation in Rack | Server installation in Rack | Server installation in Rack | Server installation in Rack | 1 | 2014-01-07 | 2014-01-08 | Comviva
|  | Switches/FW/LB Installation in Rack | Switches/FW/LB Installation in Rack | Switches/FW/LB Installation in Rack | Switches/FW/LB Installation in Rack | Switches/FW/LB Installation in Rack | Switches/FW/LB Installation in Rack | Switches/FW/LB Installation in Rack | Switches/FW/LB Installation in Rack | 1 | 2014-01-08 | 2014-01-09 | Comviva
|  | Storage/ Tape Library installation in Rack | Storage/ Tape Library installation in Rack | Storage/ Tape Library installation in Rack | Storage/ Tape Library installation in Rack | Storage/ Tape Library installation in Rack | Storage/ Tape Library installation in Rack | Storage/ Tape Library installation in Rack | Storage/ Tape Library installation in Rack | 1 | 2014-01-09 | 2014-01-10 | Comviva
|  | Cabling intra Rack between servers,switches,LB, etc | Cabling intra Rack between servers,switches,LB, etc | Cabling intra Rack between servers,switches,LB, etc | Cabling intra Rack between servers,switches,LB, etc | Cabling intra Rack between servers,switches,LB, etc | Cabling intra Rack between servers,switches,LB, etc | Cabling intra Rack between servers,switches,LB, etc | Cabling intra Rack between servers,switches,LB, etc | 1 | 2014-01-10 | 2014-01-11 | Comviva
|  | Uplink from customer backbone to Comviva platform | Uplink from customer backbone to comviva platform | Uplink from customer backbone to comviva platform | Uplink from customer backbone to comviva platform | Uplink from customer backbone to comviva platform | Uplink from customer backbone to comviva platform | Uplink from customer backbone to comviva platform | Uplink from customer backbone to comviva platform |  | 2014-01-11 | 2014-01-11 | Comviva/Orange
|  | Labeling and Dressing in Rack | Labeling and Dressing in Rack | Labeling and Dressing in Rack | Labeling and Dressing in Rack | Labeling and Dressing in Rack | Labeling and Dressing in Rack | Labeling and Dressing in Rack | Labeling and Dressing in Rack | 1 | 2014-01-11 | 2014-01-12 | Comviva
|  | Power On All devices for burning test of 24 HRS | Power On All devices for burning test of 24 HRS | Power On All devices for burning test of 24 HRS | Power On All devices for burning test of 24 HRS | Power On All devices for burning test of 24 HRS | Power On All devices for burning test of 24 HRS | Power On All devices for burning test of 24 HRS | Power On All devices for burning test of 24 HRS | 1 | 2014-01-12 | 2014-01-13 | Comviva
|  | firmware update of servers, storage and LB | firmware update of servers, storage and LB | firmware update of servers, storage and LB | firmware update of servers, storage and LB | firmware update of servers, storage and LB | firmware update of servers, storage and LB | firmware update of servers, storage and LB | firmware update of servers, storage and LB | 1 | 2014-01-13 | 2014-01-14 | Comviva
|  | IOS/firmware update in Switches | IOS/firmware update in Switches | IOS/firmware update in Switches | IOS/firmware update in Switches | IOS/firmware update in Switches | IOS/firmware update in Switches | IOS/firmware update in Switches | IOS/firmware update in Switches | 1 | 2014-01-14 | 2014-01-15 | Comviva
|  | Hardware UAT | Harware UAT | Harware UAT | Harware UAT | Harware UAT | Harware UAT | Harware UAT | Harware UAT |  | 2014-01-15 | 2014-01-15 | Comviva
[11 empty] | 2014-01-15 | 2014-01-15 | Comviva
3 | OS installation | RAID configuration in servers(10 servers) | RAID configuration in servers(10 servers) | RAID configuration in servers(10 servers) | RAID configuration in servers(10 servers) | RAID configuration in servers(10 servers) | RAID configuration in servers(10 servers) | RAID configuration in servers(10 servers) | RAID configuration in servers(10 servers) | 1 | 2014-01-15 | 2014-01-16 | Comviva
|  | OS installation as per given kick start | OS installation as per given kick start | OS installation as per given kick start | OS installation as per given kick start | OS installation as per given kick start | OS installation as per given kick start | OS installation as per given kick start | OS installation as per given kick start | 1 | 2014-01-16 | 2014-01-17 | Comviva
|  | Network configuration in servers | Network configuration in servers | Network configuration in servers | Network configuration in servers | Network configuration in servers | Network configuration in servers | Network configuration in servers | Network configuration in servers | 1 | 2014-01-17 | 2014-01-18 | Comviva
|  | Cluster Configuration in servers | Cluster Configuration in servers | Cluster Configuration in servers | Cluster Configuration in servers | Cluster Configuration in servers | Cluster Configuration in servers | Cluster Configuration in servers | Cluster Configuration in servers | 1 | 2014-01-18 | 2014-01-19 | Comviva
|  | storage integration & multipathing configuration | storage integration & multipathing configuration | storage integration & multipathing configuration | storage integration & multipathing configuration | storage integration & multipathing configuration | storage integration & multipathing configuration | storage integration & multipathing configuration | storage integration & multipathing configuration | 1 | 2014-01-19 | 2014-01-20 | Comviva
[11 empty] | 2014-01-20 | 2014-01-20 | Comviva
4 | LB Configuration | Basic Configuration | Basic Configuration | Basic Configuration | Basic Configuration | Basic Configuration | Basic Configuration | Basic Configuration | Basic Configuration | 1 | 2014-01-20 | 2014-01-21 | Comviva
|  | Configuration of policy as per services ( provided by Comviva in Deployment approach ) | Configuration of policy as per services ( provided by comviva in Deployment approach ) | Configuration of policy as per services ( provided by comviva in Deployment approach ) | Configuration of policy as per services ( provided by comviva in Deployment approach ) | Configuration of policy as per services ( provided by comviva in Deployment approach ) | Configuration of policy as per services ( provided by comviva in Deployment approach ) | Configuration of policy as per services ( provided by comviva in Deployment approach ) | Configuration of policy as per services ( provided by comviva in Deployment approach ) | 1 | 2014-01-21 | 2014-01-22 | Comviva
|  | Configuration verification | Configuration verification | Configuration verification | Configuration verification | Configuration verification | Configuration verification | Configuration verification | Configuration verification | 0.25 | 2014-01-22 | 2014-01-22 06:00 | Comviva
|  | Load Balancing configuration testing (HA/Active/Active) with application running and performance testing during load test | Load Balancing configuration testing (HA/Active/Active) with application running and performance testing during load test | Load Balancing configuration testing (HA/Active/Active) with application running and performance testing during load test | Load Balancing configuration testing (HA/Active/Active) with application running and performance testing during load test | Load Balancing configuration testing (HA/Active/Active) with application running and performance testing during load test | Load Balancing configuration testing (HA/Active/Active) with application running and performance testing during load test | Load Balancing configuration testing (HA/Active/Active) with application running and performance testing during load test | Load Balancing configuration testing (HA/Active/Active) with application running and performance testing during load test | 0.5 | 2014-01-22 06:00 | 2014-01-22 18:00 | Comviva
|  | WEB Service configuration | [7 empty] | 0.25 | 2014-01-22 18:00 | 2014-01-23 | Comviva
|  | SMSR Service Configuration | [7 empty] | 0.25 | 2014-01-23 | 2014-01-23 06:00 | Comviva
|  | SMSR Service Configuration | [7 empty] | 0.25 | 2014-01-23 06:00 | 2014-01-23 12:00 | Comviva
|  | SMPP Service Configuration | [7 empty] | 0.25 | 2014-01-23 12:00 | 2014-01-23 18:00 | Comviva
|  | IN Service Configuration | [7 empty] | 0.25 | 2014-01-23 18:00 | 2014-01-24 | Comviva
5 | Firewall Configuration | Firewall basic configuration, IPS configuration | Firewall basic configuration, IPS configuration | Firewall basic configuration, IPS configuration | Firewall basic configuration, IPS configuration | Firewall basic configuration, IPS configuration | Firewall basic configuration, IPS configuration | Firewall basic configuration, IPS configuration | Firewall basic configuration, IPS configuration | 1 | 2014-01-24 | 2014-01-25 | Comviva
|  | Access rule/Policy configuration | Access rule/Policy configuration | Access rule/Policy configuration | Access rule/Policy configuration | Access rule/Policy configuration | Access rule/Policy configuration | Access rule/Policy configuration | Access rule/Policy configuration | 0.5 | 2014-01-25 | 2014-01-25 12:00 | Comviva
|  | Integration with cluster network | Integration with cluster network | Integration with cluster network | Integration with cluster network | Integration with cluster network | Integration with cluster network | Integration with cluster network | Integration with cluster network | 0.5 | 2014-01-25 12:00 | 2014-01-26 | Comviva
|  | Configuration verification | Configuration verification | Configuration verification | Configuration verification | Configuration verification | Configuration verification | Configuration verification | Configuration verification | 0.5 | 2014-01-26 | 2014-01-26 12:00 | Comviva
|  | Hardening configuration on firewall | Hardening configuration on firewall | Hardening configuration on firewall | Hardening configuration on firewall | Hardening configuration on firewall | Hardening configuration on firewall | Hardening configuration on firewall | Hardening configuration on firewall | 0.5 | 2014-01-26 12:00 | 2014-01-27 | Comviva
[11 empty] | 2014-01-27 | 2014-01-27 | Comviva
6 | Switch Configuration | Switch configuration | Switch configuration | Switch configuration | Switch configuration | Switch configuration | Switch configuration | Switch configuration | Switch configuration | 1 | 2014-01-27 | 2014-01-28 | Comviva
|  | Vlan configuration | Vlan configuration | Vlan configuration | Vlan configuration | Vlan configuration | Vlan configuration | Vlan configuration | Vlan configuration | 1 | 2014-01-28 | 2014-01-29 | Comviva
|  | routing configuration | routing configuration | routing configuration | routing configuration | routing configuration | routing configuration | routing configuration | routing configuration | 0.5 | 2014-01-29 | 2014-01-29 12:00 | Comviva
|  | Hardening configuration on switches | Hardening configuration on switches | Hardening configuration on switches | Hardening configuration on switches | Hardening configuration on switches | Hardening configuration on switches | Hardening configuration on switches | Hardening configuration on switches | 0.5 | 2014-01-29 12:00 | 2014-01-30 | Comviva
[11 empty] | 2014-01-30 | 2014-01-30 | Comviva
7 | Hardening | OS Hardening as per FT document | Firewall basic configuration, IPS configuration | Firewall basic configuration, IPS configuration | Firewall basic configuration, IPS configuration | Firewall basic configuration, IPS configuration | Firewall basic configuration, IPS configuration | Firewall basic configuration, IPS configuration | Firewall basic configuration, IPS configuration | 5 | 2014-01-30 | 2014-02-04 | Comviva
[11 empty] | 2014-02-04 | 2014-02-04 | Comviva
8 | External storage | firmware Update in Storage | firmware Update in Storage | firmware Update in Storage | firmware Update in Storage | firmware Update in Storage | firmware Update in Storage | firmware Update in Storage | firmware Update in Storage | 1 | 2014-02-04 | 2014-02-05 | Comviva
|  | Network and hostname configuration | Network and hostname configuration | Network and hostname configuration | Network and hostname configuration | Network and hostname configuration | Network and hostname configuration | Network and hostname configuration | Network and hostname configuration | 1 | 2014-02-05 | 2014-02-06 | Comviva
|  | firmware Update in Storage | firmware Update in Storage | firmware Update in Storage | firmware Update in Storage | firmware Update in Storage | firmware Update in Storage | firmware Update in Storage | firmware Update in Storage | 0.5 | 2014-02-06 | 2014-02-06 12:00 | Comviva
|  | Network and hostname configuration | Network and hostname configuration | Network and hostname configuration | Network and hostname configuration | Network and hostname configuration | Network and hostname configuration | Network and hostname configuration | Network and hostname configuration | 0.5 | 2014-02-06 12:00 | 2014-02-07 | Comviva
9 | Database Activities | DB Verification | [7 empty] | 0.5 | 2014-02-07 | 2014-02-07 12:00 | Comviva
|  | Oracle Installation /Database & Schema Creation/Table space creation | [7 empty] | 1 | 2014-02-07 12:00 | 2014-02-08 12:00 | Comviva
|  | Data Import from the dump taken from Production Database | [7 empty] | 0.5 | 2014-02-08 12:00 | 2014-02-09 | Comviva | DB export dump required from production system.
|  | DB Cluster Integration | [7 empty] | 1 | 2014-02-09 | 2014-02-10 | Comviva
|  | Perform PLSQL DB load testing. | [7 empty] | 1 | 2014-02-10 | 2014-02-11 | Comviva
|  | Schedule cronjobs/Tape Backup/Net backup | [7 empty] | 0.5 | 2014-02-11 | 2014-02-11 12:00 | Comviva
|  | DB Backup testing | [7 empty] | 0.5 | 2014-02-11 12:00 | 2014-02-12 | Comviva
10 | Application Deployment & Integration Pretups 6X | WEB Application Deployment/Configuration on WEB Server Pretups 6x | [7 empty] | 4 | 2014-02-12 | 2014-02-16 | Comviva
|  | SMSR/SMSP Application Deployment/Configuration on Transaction servers Pretups 6x | [7 empty] | 5 | 2014-02-16 | 2014-02-21 | Comviva
|  | OAM Configuration. | [7 empty] | 1 | 2014-02-21 | 2014-02-22 | Comviva
|  | RP Service Configuration | [7 empty] | 4 | 2014-02-22 | 2014-02-26 | Comviva
|  | Integration of SMSR/SMSP with IN | [7 empty] | 1 | 2014-02-26 | 2014-02-27 | Comviva
|  | Integration of SMSR/WEB with HLB | [7 empty] | 1 | 2014-02-27 | 2014-02-28 | Comviva
|  | Integration of WEB and SMSR/SMSP Application with SMSC | [7 empty] | 1 | 2014-02-28 | 2014-03-01 | Comviva
|  | Integration of WEB and SMSR/SMSP Application with Syslog-ng | [7 empty] | 1 | 2014-03-01 | 2014-03-02 | Comviva
|  | Application testing (SMSR, SMSP and WEB) | [7 empty] | 5 | 2014-03-02 | 2014-03-07 | Comviva
11 | Application Load Testing | Internal Application load testing with IN Simulator | [7 empty] | 3 | 2014-03-07 | 2014-03-10 | Comviva
|  | Application Load testing with Live IN | [7 empty] | 2 | 2014-03-10 | 2014-03-12 | Comviva/Orange
12 | UAT | UAT Test case execution by Client | [7 empty] | 5 | 2014-03-12 | 2014-03-17 | Comviva/Orange
13 | Hardware Handover UAT | Hardware Handover UAT | [7 empty] | 5 | 2014-03-17 | 2014-03-22 | Comviva/Orange
14 | UAT Signoff | Signoff of UAT document by Client | [7 empty] | 0 | 2014-03-22 | 2014-03-22 | Comviva/Orange
16 | Trial Migration | Take import from Production Live DB | [7 empty] | 0.5 | 2014-03-22 | 2014-03-22 12:00 | Comviva
|  | Copy the dump from Production DB server to DR DB Server | [7 empty] | 0.5 | 2014-03-22 12:00 | 2014-03-23 | Comviva
|  | Import Dump in DR Database | [7 empty] | 0.5 | 2014-03-23 | 2014-03-23 12:00 | Comviva
|  | Test Application with new data (Testing of recharge with new Data) | [7 empty] | 1 | 2014-03-23 12:00 | 2014-03-24 12:00 | Comviva
17 | Migration | Final Migration | [7 empty] | 1 | 2014-03-24 12:00 | 2014-03-25 12:00 | Comviva/Orange
18 | Monitoring Period | [8 empty] | 0 | 2014-03-25 12:00 | 2014-03-25 12:00 | Comviva
83.5
Formulas:
End Date = [Start Date]+[Man Days Required]
Start Date = [End Date, row above]

## Revision History
Onsite Status Report
Internal Use
Revision History
Issue No. | Revision No. | Release Date | Change Description | Prepared By | Reviewed By | Approved By
A | 0.1 | 2014-08-25 | Initial Draft

## Loading
Hardware Installation | 10%
OS installation | 5%
Network Configuration | 15%
Security and Hardening | 5%
External storage | 5%
Database Activities | 10%
WEB Application Deployment | 10%
SMSR/SMSP Application Deployment | 20%
OAM Configuration | 10%
Load Testing | 5%
Trial Migration | 5%

## Activity Loading
Hardware Installation | 10%
OS installation | 5%
Network Configuration | 15%
Security and Hardening | 5%
External storage | 5%
Database Activities | 10%
WEB Application Deployment | 10%
SMSR/SMSP Application Deployment | 20%
OAM Configuration | 10%
Load Testing | 5%
Trial Migration | 5%
PENDING | 0%

## Sheet3
S. No | TASK | Cumm Planned | Cumm Actual | Man Days Planned | Man Days Actual
1 | Hardware Installation - | 11 | 2 | 11 | 2
2 | OS installation | 17 | 2 | 6 | 0
3 | LB Configuration | 25.25 | 2 | 8.25 | 0
4 | Firewall Configuration | 28.25 | 2 | 3 | 0
5 | Switch Configuration | 32.25 | 2 | 4 | 0
6 | Security & Hardening | 35.25 | 2 | 3 | 0
7 | External storage | 39.25 | 2 | 4 | 0
8 | Database Activities | 49.75 | 2 | 10.5 | 0
9 | WEB Application Deployment/Configuration on WEB Server Pretups 6x X 2 | 97.25 | 2 | 47.5 | 0
10 | SMSR/SMSP Application Deployment/Configuration on Transaction servers Pretups 6x | 100.25 | 2 | 3 | 0
11 | OAM Configuration | 100.75 | 2 | 0.5 | 0
12 | Integration of SMSR/SMSP with IN | 101.75 | 2 | 1 | 0
13 | Integration of SMSR/WEB with HLB | 102.75 | 2 | 1 | 0
14 | Integration of WEB and SMSR/SMSP Application with SMSC | 103.75 | 2 | 1 | 0
15 | Integration of WEB and SMSR/SMSP Application with Syslog-ng | 104.75 | 2 | 1 | 0
16 | Application testing (SMSR, SMSP and WEB) | 109.75 | 2 | 5 | 0
17 | Application Load Testing | 114.75 | 2 | 5 | 0
18 | UAT | 119.75 | 2 | 5 | 0
19 | Hardware Handover UAT | 124.75 | 2 | 5 | 0
20 | UAT Signoff | 124.75 | 2 | 0 | 0
21 | DR Configuration & Load Test. | 124.75 | 2 | 0 | 0
22 | Trial Migration | 124.75 | 2 | 0 | 0
23 | Migration | 125.75 | 2 | 1 | 0
24 | Monitoring Period | 125.75 | 2 | 0 | 0
25 | DR Drill ( Primary to DR ) | 126.75 | 2 | 1 | 0
26 | DR Drill ( DR to Primary ) | 127.75 | 2 | 1 | 0
27 | Monitoring Period. | 127.75 | 2 | 0 | 0