Project Implementation Lifecycle

Table of Contents

1 Document Overview	1-2

1.1	Purpose	1-3

1.2	Scope	1-3

1.3	Definitions, Acronyms and Abbreviations	1-3

1.4	Audience	1-3

1.5	References	1-3

2 Process Flow	2-4

2.1	Implementation Life cycle	2-5

2.2	Pre-requisite for Solution Specification	2-5

2.3	Documents to be prepared by Domain SME	2-6

2.4	Check-list for site readiness	2-6

2.5	Pre-requisites for resource mobilization	2-7

2.6	System UAT	2-7

Figures

Figure 2-1: Process Flow	2-5

Figure 2-2: Network Architecture	2-7

Tables

Table 2-5: Pre-requisites  for resource mobilization for platform deployment	2-7

DOCUMENT CONTROL

| Version | Date | Author/Reviewer/Approver | Summary of Changes |
| --- | --- | --- | --- |

Revision history

| Author | Change Date | Change content | Resulting release |
| --- | --- | --- | --- |

# Document Overview

## Purpose

The purpose of the document is to define the process of complete project implementation lifecycle. This would also include but not limited to the pre-requisite for solution specification, check-list for site readiness, Pre-requisite for sending an implementation engineer onsite and verification of the received hardware.

## Scope

This document defines the project implementation process and the scope consists of :

- Pre-requisite for Solution specification from DPM and PU

- Check-list for site readiness

- Pre-requisite check-list before sending an implementation engineer at site

- Hardware verification check-list at site

## Definitions, Acronyms and Abbreviations

| - Acronym | - Defination |
| --- | --- |
| - PO | - Purchase Order |
| - OAR |  |
| - SRB | - S Review Board |
| - PIC | - Pre-installation check-list |
| - SRM | - S Review Manager |
| - SOW | - Statement of Work |
| - UAT | - User Acceptance Test |
| - PU | - Product Unit |
| - DPM | - Delivery Project Management |

## Audience

- This document is intended for Implementation Team.

## References

- None

# Process Flow

## Implementation Life cycle

- The below process flow explains the complete life cycle for implementation process. It clearly segregates the tasks of Program Management, SRB and Implementation Manager.

- The process starts as soon as PO is received. OAR is generated by DPM and a client kick-off meeting is scheduled for discussion on exact requirements and necessary detail required. This kick-off meeting is attended by Client, DPM, SME for required domains.

- An initial list of documents is provided by DPM which are reviewed and further built in details for each domain involved in the project.

Figure 2-1: Process Flow

## Pre-requisite for Solution Specification

Below documents need to be provided by DPM to the Implementation group to understand the customer requirements and the agreed solution overview with customer. This information should be required before-hand to build domain specific solution document by the Implementation team.

- Final BOM

- Agreed SOW with customer

- Detailed Deployment approach with proposed architecture for this solution from PU

- Technical proposal shared and RFP response shared with customer

## Documents to be prepared by Domain SME

On receipt of the above mentioned documents from DPM and PU Group, it is the responsibility for the domain SME to create below documents.

- PIC

- Solution Implementation document/configuration document

- Network Architecture diagram (Domain Specific)

- Audit/Action Tracker

- Test Cases ( Platform test cases by Implementation and App by PVG/PU )

## Check-list for site readiness

- The attached sheet mentions the check-list for sit readiness before deployment can be initiated. The list covers check points for customer contact details at site, physical requirements, Data Center/Facilities requirement, Network requirements etc. The scope of the list attached is not limited to information documented. Points can be added as per the requirement. This would also include the PIC created by SMEs for their respective domains.

## Pre-requisites for resource mobilization

The below list provides the check-list of pre-requisites points/tasks that should to be completed before an Implementation Engineer is sent to the site. This would lower our implementation time by reducing time that is wasted in waiting for the site to be implementation-ready.

Table 2-5: Pre-requisites  for resource mobilization for platform deployment

| Sr No | Pre-requisites | Status | Artefacts | Remarks |
| --- | --- | --- | --- | --- |
| 1 | Rack space allocation inside datacenter | Open/Closed |  |  |
| 2 | Complete hardware availability at Data Centre ( Installation site) | Open/Closed |  |  |
| 3 | Final comparison sheet between Packing list and agreed final BOM with customer | Open/Closed |  |  |
| 4 | Power Availability form two redundant sources in Rack | Open/Closed |  |  |
| 5 | Confirmation of Tile cutting at allocated Rack space | Open/Closed |  |  |
| 6 | IP Pools allocation | Open/Closed |  |  |
| 7 | Uplink cables from Customer Rack to Comviva rack on Ethernet drop | Open/Closed |  |  |
| 8 | Remote connectivity | Open/Closed |  |  |
| 9 | Filled PIC | Open/Closed |  |  |

Figure 2-2: Network Architecture

## System UAT

The attached list mentions test tasks (not limited to) that need to be performed for user acceptance. The list can be modified as per specific customer requirements. The sheet mentions the ideal expected results and the actual results with outputs.

## Detailed activity plan

## MBSS (minimum baseline security   standard) template

## Network implementation template

## PPIC (Platform Pre installation checklist) template

## Pre-requisite from PU