## Slide 1
Platform Preparedness Effort Estimation
Feb – 2018

## Slide 2: Agenda
Objective
Project Categorization
Activities Considered (In Scope & Out of Scope)
Planned Efforts
Pre-requisite/Support Required

## Slide 3: Objective
Reduce the Delivery Cost of the Project by
    Reducing.
      The onsite stay
      Avoid rework
      The idle days in onsite stay.
      Number of onsite travel @ project.
    Structured approach for
      Platform readiness
      Improved ownership for H/w UAT

## Slide 4
Project Categorization For Platform deployment
Nodes | Tiny | Small | Medium | Large
DB Server | 2 | 2 | 2 | 3
Txn server | 2 | 2 | 4 | 4
Webserver | 1 | 2 | 4 | 4
Firewall | 0 | 0 | 0 | 0
LB | 0 | 0 | 2 | 2
Storage | 1 | 1 | 1 | 1
SAN switch | 0 | 2 | 2 | 2
LAN switch | 2 | 2 | 4 | 8
Tape library | 0 | 0 | 1 | 1
Backup server | 0 | 0 | 1 | 1
Test server | 0 | 1 | 1 | 1
Staging DB server | 0 | 1 | 1 | 1
Staging App server | 0 | 0 | 1 | 1
Logging server | 0 | 0 | 1 | 2
Reporting server | 0 | 0 | 1 | 1
USSD app server | 0 | 1 | 1 | 2
USSD DB server | 0 | 1 | 1 | 2
USSD test server | 0 | 1 | 0 | 1
VM management console | 1 | 1 | 1 | 1
RACK 1 | 1 | 1 | 2 | 3
Total | 10 | 18 | 31 | 41
Type | No of Nodes | Switches | Rack
Tiny | 1-7 | 2 | 1
Small | 8-15 | 2 | 1
Medium | 15-25 | 4 | 2
Large | >25 | 8 | 3

## Slide 5
S. No. | Activity
1 | Site survey and PIC preparation
2 | Prerequisites Check Up (onsite activity) & Rack installation
3 | Hardware Installation - Servers, Switches, Storage and Tape Drives
4 | Storage configuration -
5 | Load Balancer Configuration
6 | Network configuration (Firewall and Switches)
7 | QAT Preparation ( labelling , cabling & Dressing
8 | Operating System Installation
9 | Security hardening
10 | Backup , SNMP configuration , HW UAT
In Scope Activities
S. No. | Activity
1 | Activity Duration shall start only after availability of Complete Hardware at the datacentre.
2 | Enabling the VPN connectivity between Comviva IT and Customer IT
3 | Power installation , uplink connection at customer end
4 | Database installation/creation Application/database Migration activities, load testing , performance tuning
5 | SNOC and Security audit clearance
6 | Change in Scope
7 | Stabilization effort in new technology adoption
Out of Scope Activities
Activities Considered (In Scope & Out of Scope)

## Slide 6: Planned Efforts – Deployment on Physical Hardware
Components - Platform | Tiny | Small | Medium | Large
# Offsite OLPS & SSPO UAT | 14 | 14 | 24 | 30
# Post Installation Documentation | 5 | 5 | 5 | 5
Ready for UAT
UAT with OLPS and SSPO Additional for Orange
Components - HW , OS, N/w & Security | Tiny | Small | Medium | Large
Person Days (effort) (Onsite + Offsite) | 25 | 26 | 35 | 30
# No. of Round Trips | 1 | 1 | 2 | 2
# No. of Onsite Stay (days) | 8 | 9 | 12 | 17
# No. of Offsite days Offsite days for support during implementation Documentation security clearance Till go-live support | 2 5 5 5 | 2 5 5 5 | 2 7 7 7 | 4 7 9 9

## Slide 7: Planned Efforts Virtual Setup – Based on Project Categorization
Ready for UAT
UAT with OLPS and SSPO Additional for Orange
Components - HW , VM, OS, N/w & Security (A) | Tiny | Small | Medium | Large
Person Days (effort) (Onsite + Offsite + Training) | 31 | 32 | 43 | 55
# No. of Round Trips | 1 | 1 | 2 | 2
# No. of Onsite Stay (days) | 10 | 11 | 15 | 21
# No. of Offsite days Offsite days for support during implementation Documentation security clearance Till go-live support | 4 5 5 5 | 4 5 5 5 | 4 7 7 7 | 6 7 9 9
# Training on Virtualization to customer (Onsite) | 2 | 2 | 3 | 3
Components - Platform | Tiny | Small | Medium | Large
# Offsite OLPS & SSPO UAT | 14 | 14 | 24 | 30
# Post Installation Documentation | 5 | 5 | 5 | 5

## Slide 8: Planned Efforts with OS, Network & VM – HW excluded
Components - HW , OS, N/w & Security | Tiny | Small | Medium | Large
Person Days (effort) (Onsite + Offsite) | 26 | 27 | 33 | 44
# No. of Round Trips | 1 | 1 | 1 | 1
# No. of Onsite Stay (days) | 5 | 6 | 8 | 13
# No. of Offsite days Offsite days for support during implementation Documentation security clearance Till go-live support | 6 5 5 5 | 6 5 5 5 | 6 5 7 7 | 8 5 9 9
Components - Platform | Tiny | Small | Medium | Large
# Offsite OLPS & SSPO UAT | 14 | 14 | 24 | 30
# Customize Documentation | 5 | 5 | 5 | 5
UAT with OLPS and SSPO Additional for Orange
Ready for UAT

## Slide 9: Planned Efforts for Audit – Based on Project Categorization
Components - HW , OS, N/w & Security | Tiny | Small | Medium | Large
Person Days (Offsite) | 3 | 4 | 5 | 6
# No. of Round Trips | 0 | 0 | 0 | 0
Pre Go-Live Audit

## Slide 10: Pre-requisite/Support Required
S. No. | Pre-requisite | Responsibility
1 | No travel shall be initiated before completion of Site readiness Check list (Attached) | Project Manager
2 | Following Items required during project kick off Deployment planning Checklist (Attached) Solution Document for Platform Deployment (Attached) | Project Manager/PU

## Slide 11
Thank You