## Complete installation
Objective
The document contains the activities to be performed completely by third party vendor for H/W and S/W installation. The objective of the document is to provide the onsite team complete visibility with respect to the installation activities. The document shall cover installations of applicable devices but the vendor is expected to work beyond the scope mentioned in the document, to achieve success in the project.
S.No. | Complete installation Scope of Work | Remarks
1 Prerequisites Check Up
1.1 | Survey of Implementation Site, as per site survey check list.
1.2 | Physical Verification H/W as per shipment packing list. | BOQ & Packing list will be provided by PM
1.3 | Physical Verification of Bill of Material (BOM)
1.4 | Un-Packaging of Hardware at Installation Site & Assemble server
1.5 | Cross-Checking With Packing List
1.6 | Rack installation and placement
2 Hardware Installation-Servers, Switches, Storage and Tape Drives
2.1 | Mounting of hardware in Rack such as HP PDU, Chassis, and Server Storage.
2.2 | Powering-On hardware devices.
2.3 | Blade server / Rack Server Add-on component configuration. Such as – HBA Card/ NIC Card/ RAID Controller.
2.4 | Update latest Firmware and BIOS.
2.5 | Configure ILO / Management IP as per shared IP document.
2.6 | Chassis Onboard Administrator configuration as per shared document.
2.7 | Chassis BNT Switch configuration as per shared document.
2.8 | Chassis VC flex switch configuration as per shared document.
2.9 | Chassis SAN switch configuration / Zoning as per shared document.
2.10 | Power on Self-Test (POST).
2.11 | Proper Cabling of all rack mountable device.
2.12 | Proper Labeling of all rack Mountable device and cable.
2.13 | All device Hardware Configuration backup
3 Operating System Pre and Post Installation
3.1 | Installation of Operating System (As Per The Comviva Document)
3.2 | Installation of RHEL Packages (As Per Partition Document Provided By COMVIVA)
3.3 | Installation of RHEL OS(Refer the Solution document for OS version)
3.4 | Configuration of IP Address in hardware (As Per Document Provided By COMVIVA)
4 Configuration - Infrastructure, Application
4.1 | YUM Configuration
4.2 | Network Configuration on Servers
4.3 | NTP configuration
4.4 | syslog-ng installation (Based on the Project)
4.5 | Antivirus Installation In Linux Server (Based on the Project)
4.6 | Java installation (Based on the Project)
4.7 | Physical connectivity of Servers, Storage with Network switches
4.8 | Creation of LUNs in Storage, Mapping and mounting of LUNs in
4.9 | Multipathing
4.10 | Configuration of RHEL Cluster in servers.(As Per COMVIVA application team requirement)
4.11 | Server OS hardening.
4.12 | Switch configuration
4.13 | Firewall configuration
4.14 | Cabling
4.15 | labeling
5 Final Testing - Infrastructure, Application & Documentation
5.1 | Checking and verifying Server, Storage
5.2 | Checking and verifying Network Switches and Connectivity
5.3 | OS Hardening & Tuning
5.4 | Testing of Complete Infrastructure (Cluster, network and power of servers and rest hardware )
5.5 | Labeling of Components, Cable tying and dressing
5.6 | Snapshot of Installed Hardware After Integration & Labeling
5.7 | Final testing of all hardware and software
5.8 | Handover of configuration Document to Comviva in Mahindra Comviva format