## EMC
Objective
The document contains the activities to be performed by third party vendor for H/W and S/W installation of EMC The objective of the document is to provide the onsite team complete visibility with respect to the installation activities. The document shall cover installations of applicable devices but the vendor is expected to work beyond the scope mentioned in the document, to achieve success in the project.
S.No. | EMC Scope of Work | Remarks
1 Prerequisites Check Up
1.1 | Verification of Compatibility of Hardware
1.2 | Validation of EMC and server hardware compatibility along with OS version
1.3 | Validation of OS kernel compatibility, Patch set may be required for this specific release of hardware using the Redhat site and vendor release note.
1.4 | Verify EMC BOX as per BOQ/Packing List. | BOQ & Packing list will be provided by PM
1.5 | Collecting of All devices Serial number, Make, Model Details.
2 EMC Installation & Configuration
2.1 | Mounting of storage in the Rack.
2.2 | Powering-On storage. | Power requirement must be verified
2.3 | Updating the Firmware & Software Versions of the Storage.
2.4 | Validation of OS kernel compatibility with EMC version. To register SAN/NAS host agent.
2.5 | Ensure the firmware and BIOS is latest and updated.
2.6 | Verification of Firmware version
2.7 | Ensure the updated firmware of device with authenticated documents released by principle manufacturer(EMC) of hardware.
2.8 | 24 hrs Power ON Hardware burning test
2.9 | Verify WWN Number according to the host.
2.10 | SAN switch zone configuration for EMC and Servers.
2.11 | Configuration of RAID and logical drive. As per partition document provided by MComviva during the installaion. | Partition document will be provided by Solutioing team
2.12 | Host agent binary installtion in server.
2.13 | HOST mapping according to the shared document.
2.14 | Verification & performance testing of Mount Points | testing steps will be provided by solutioing/implementation team
2.15 | Labeling and dressing of EMC storage .
2.16 | Handover of configuration Document to Comviva in Mahindra Comviva format