## Generic Hardware Installation
Objective
The document contains the activities to be performed by third party vendor for H/W and Firmware installation onsite. The objective of the document is to provide the onsite team complete visibility with respect to the installation activities. The document shall cover installations of applicable devices but the vendor is expected to work beyond the scope mentioned in the document, to achieve success in the project.
S.No. | Generic Hardware Installation Scope of Work | Remarks
1 Prerequisites Check Up
1.1 | Verify Hardware component according to the BOQ Document and packing list.. | BOQ & Packing list will be provided by PM
1.2 | Collect all devices Serial Number, Model Number.
1.3 | Need to collect Rack Name and Rack Position Number.
2 Hardware Installation-Chassis ,Servers.
2.1 | Mounting of hardware in Rack such as HP PDU, Chassis, and Server Storage.
2.2 | Powering-On hardware devices. | Power requirement must be verified
2.3 | Blade server / Rack Server Add-on component configuration. Such as – HBA Card/ NIC Card/ RAID Controller.
2.4 | Update latest Firmware and BIOS.
2.5 | Configure ILO / Management IP as per shared IP document.
2.6 | Chassis Onboard Administrator configuration as per shared document.
2.7 | Chassis BNT Switch configuration as per shared document.
2.8 | Chassis VC flex switch configuration as per shared document.
2.9 | Chassis SAN switch configuration / Zoning as per shared document.
2.10 | Power on Self-Test (POST).
2.11 | Proper Cabling of all rack mountable device.
2.12 | Proper Labeling of all rack Mountable device and cable.
2.13 | All device Hardware Configuration backup
2.14 | Handover of configuration Document to Comviva in Mahindra Comviva format