## SUN Product SOW
Objective
The document contains the activities to be performed completely by third party vendor for SUN H/W and S/W installation. The objective of the document is to provide the onsite team complete visibility with respect to the installation activities. The document shall cover installations of applicable devices but the vendor is expected to work beyond the scope mentioned in the document, to achieve success in the project.
S.No. | SUN installation Scope of Work | Remarks
1 Prerequisites Check Up
1.1 | Survey of Implementation Site, as per site survey check list.
1.2 | Physical Verification H/W as per shipment packing list. | BOQ & Packing list will be provided by PM
1.3 | Physical Verification of Bill of Material (BOM)
1.4 | Un-Packaging of Hardware at Installation Site & Assemble server
1.5 | Cross-Checking With Packing List
1.6 | Rack installation and placement
2 Hardware Installation-Servers, Switches, Storage and Tape Drives
2.1 | Integration of add-on Components (HBA cards, CPU, RAM, Hard Disks etc.)
2.2 | Mounting of all The Hardware in the Rack
2.3 | Powering on The Servers and Initial Testing
2.4 | Updating The Firmware & BIOS Versions of The Servers
2.5 | Configuration of RAID & Logical Drive (As Per Partition Document Provided By COMVIVA)
2.6 | Powering on the Servers, storage & Testing of All Hardware after Integration | Power requirement must be verified
3 Operating System Pre and Post Installation
3.1 | SUN Solaris 11.X in server.
3.2 | Latest Kernel and Errata updates
3.3 | LAN Interface redundancy (IPMP Active-backup) configuration.
3.4 | Hostname & IP configuration.
3.5 | PKG configuration in all servers.
3.6 | Distribution of LDOM on Physical Servers as per the LDOM architecture
3.7 | Configuration of Kernel tuning parameters
4 Configuration - Infrastructure, Application
4.1 | Network Configuration on Servers
4.2 | NTP configuration
4.3 | syslog-ng installation (Based on the Project)
4.4 | Java installation
4.5 | Physical connectivity of Servers, Storage with Network switches
4.6 | Creation of LUNs in Storage, Mapping and mounting of LUNs in
4.7 | SUN Native Multipath configuration and Storage LUN mounting.
4.8 | Configuration of RHEL Cluster in servers.(As Per COMVIVA application team requirement)
4.9 | Configuration of Routes and establish connectivity with integration points.
4.10 | Server OS hardening.
5 Final Testing - Infrastructure, Application & Documentation
5.1 | Checking and verifying Server , Storage
5.2 | Checking and verifying SAN Switches, Storage - Server Connectivity
5.3 | OS Hardening & Tuning
5.4 | Testing of Complete Infrastructure (Cluster, network and power of servers and rest hardware )
5.5 | Labeling of Components, Cable tying and dressing
5.6 | Snapshot of Installed Hardware After Integration & Labeling
5.7 | Final testing of all hardware and software
5.8 | Handover of configuration Document to Comviva in Mahindra Comviva format