## New_installation
S No | Stages | Responsibility | Time required to complete the task | Remarks
1 | Prerequisites Check Up
1.1 | Physical Verification of Bill of Material (BOM) | SI- Thirdparty vendor
1.2 | Un-Packaging of Hardware at Installation Site | SI- Thirdparty vendor
1.3 | Cross-Checking With Packing List | SI- Thirdparty vendor
1.4 | Rack installation and placement check against the solution document | SI- Thirdparty vendor
2 | Hardware Installation - Servers, Switches, Storage and Tape Drives
2.1 | Intergation of add-on Components (HBA cards, CPU, RAM, Hard Disks etc.) | SI- Thirdparty vendor
2.2 | Mounting of all The Hardware in the Rack | SI- Thirdparty vendor
2.3 | Powering on The Servers and Initial Testing | SI- Thirdparty vendor
2.4 | Updating The Firmware & BIOS Versions of The Servers | SI- Thirdparty vendor
2.5 | Configuration of fencing and net MGMT Servers | SI- Thirdparty vendor
2.6 | Configuration of RAID & Logical Drive (As Per Solution document PIC) | SI- Thirdparty vendor
2.7 | Powering on the Servers, Switches & Testing of All Hardware after Integration | SI- Thirdparty vendor
3 | Storage configuration
3.1 | Intergation of add-on Components (HBA modules, Hard Disks etc.) | SI- Thirdparty vendor
3.2 | Mounting of all The Hardware in the Rack | SI- Thirdparty vendor
3.3 | Powering on The Storage and Initial Testing | SI- Thirdparty vendor
3.4 | Updating The Firmware & BIOS Versions ofcontroller/disk | SI- Thirdparty vendor
3.5 | RAID configuration as per Solution document PIC | SI- Thirdparty vendor
3.6 | LUN creation and presentation of LUN on respective hosts and applicable security hardening | SI- Thirdparty vendor
4 | LB configuration
4.1 | Physical mounting in RACK | SI- Thirdparty vendor
4.2 | Basic Configuration | SI- Thirdparty vendor
4.3 | Configuration of policy as per services ( provided by comviva in Deployment approach ) | SI- Thirdparty vendor
4.4 | Configuration verification | SI- Thirdparty vendor
4.5 | Load Balancing testing (HA/Active/Active) | SI- Thirdparty vendor
4.6 | Security hardening | SI- Thirdparty vendor
5 | Network configuration
5.1 | Firewall installation , IPS configuration | SI- Thirdparty vendor
5.2 | Access rule/Policy configuration | SI- Thirdparty vendor
5.3 | Integration with custer network | SI- Thirdparty vendor
5.4 | Configuration verification | SI- Thirdparty vendor
5.5 | Security hardening | SI- Thirdparty vendor
6 | Operating System Installation
6.1 | Installation of Operating System (As Per Solution document) | SI- Thirdparty vendor
6.2 | Installation of OS Packages (As Per Solution document) | SI- Thirdparty vendor
6.3 | Security hardening and Kernel update . | SI- Thirdparty vendor
6.4 | Configuration of IP Address (As Per Solution document PIC) | SI- Thirdparty vendor
7 | Initial Infrastructure Testing
7.1 | Checking and verifying DB, Media & Signalling server | SI- Thirdparty vendor
7.2 | Checking and verifying Application server | SI- Thirdparty vendor
7.3 | Checking and verifying External Storage | SI- Thirdparty vendor
7.4 | Checking and verifying Tape Drives and connectivity | SI- Thirdparty vendor
7.5 | Checking and verifying Network Switches and Connectivity | SI- Thirdparty vendor
7.6 | Checking and verifying All Rack Hardware and connectivity | SI- Thirdparty vendor
8 | Backup and restoration configuration
8.1 | Instalation of Backup software | SI- Thirdparty vendor
8.2 | Policy configuration | SI- Thirdparty vendor
8.3 | Verification and testing of Backup and restore | SI- Thirdparty vendor
8.4 | Backup and restoration configuration | SI- Thirdparty vendor
8.5 | Verification of configuration | SI- Thirdparty vendor
8.6 | Security Hardening | SI- Thirdparty vendor
9 | Security Hardening
9.1 | Vuleneribility accessment | SI- Thirdparty vendor
9.2 | Remedial action post VA | SI- Thirdparty vendor
9.3 | Security clearnace from Airtel Infosec Team | SI- Thirdparty vendor
9.4 | Security sign-off | SI- Thirdparty vendor
10 | Documentation Required
10.1 | Testing of Complete Infrastructure (Operating System, Hardware HA) | SI- Thirdparty vendor
10.2 | Labeling of Components, Cable tying and dressing | SI- Thirdparty vendor
10.3 | Snapshot of Installed Hardware After Integration & Labeling | SI- Thirdparty vendor
10.4 | Configuration Backup & Documentation (SysReport, Hostname, IP Address Details, Hardware Report & Passwords) | SI- Thirdparty vendor
11 | Hardware UAT
11.1 | As per the UAT Document | SI- Thirdparty vendor
12 | UAT Signoff | Comviva/Customer
13 | Handover to C omviva | Internal
14 | Project Clouser | Internal